## PMR
Civil Service Commission RO VIII | [11 empty] | Procurement Monitoring Report as of December 31, 2023
[5 empty] | Actual Procurement Activities | [20 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column1 | Column2
COMPLETED PROCUREMENT ACTIVITIES | [31 empty] | -
|  | ESD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-05-31 |  | 2023-05-31 | N/A | 2023-05-31 |  | 0 | [8 empty] | Government of the Philippines (current year's budget) | 0 |  |  | 12725 | 12725 |  | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
|  | MSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-05-31 |  | 2023-05-31 | N/A | 2023-05-31 | [10 empty] | Government of the Philippines (current year's budget) | 0 |  |  | 3813.6 | 3813.6
[26 empty] | 0 |  |  | 0
|  | ESD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A |  | 2023-06-20 |  | 2023-06-20 | N/A | 2023-06-20 |  |  |  | 2023-06-23 | 2023-06-23 | 2023-06-23 |  |  | 2023-06-27 | 2023-06-27 | Government of the Philippines (current year's budget) | 1275 | 1275 |  | 1275 | 1275 | [9 empty] | Completed
1 | Office Supplies (Ink for Brother Printers and Additional Exam Supplies)-HBC Enterprises | MSD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | N/A | 2023-06-13 |  | 2023-06-13 | N/A | 2023-06-13 |  |  |  | 2023-06-26 | 2023-06-27 | 2023-06-27 |  |  | 2023-07-03 | 2023-07-03 | Government of the Philippines (current year's budget) | 48750 | 48750 |  | 48125 | 48125 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
2 | Office Supplies-Ink for Brother Printers and Additional Exam Supplies (Paper Mimeo,A4 10 Reams and Legal 30 Reams)-Leyte Paperworld | MSD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | N/A | 2023-06-13 |  | 2023-06-13 | N/A | 2023-06-13 |  |  |  | 2023-06-26 | 2023-06-26 | 2023-06-26 |  |  | 2023-07-02 | 2023-07-02 | Government of the Philippines (current year's budget) | 13600 | 13600 |  | 7273 | 7273 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
3 | 2 Burner Gas Stove | FONS | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-06-13 |  | 2023-06-13 | N/A | 2023-06-13 |  |  |  | 2023-06-27 | 2023-06-27 | 2023-06-27 |  |  | 2023-07-11 | 2023-07-11 | Government of the Philippines (current year's budget) | 2000 | 2000 |  | 1285 | 1285 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
4 | Office Supplies 1st Quarter (RMC Trading) | MSD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | N/A | 2023-05-23 |  | 2023-05-23 | N/A | 2023-05-23 |  |  |  | 2023-06-30 | 2023-07-03 | 2023-07-03 |  |  | 2023-07-18 | 2023-07-18 | Government of the Philippines (current year's budget) | 115205.6 | 115205.6 |  | 102150 | 102150 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5 | Office Supplies 1st Quarter (Broom, Soft and Record Book, 30 pieces) Tac Tap Commercial | MSD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | N/A | 2023-05-23 |  | 2023-05-23 | N/A | 2023-05-23 |  | 0 |  | 2023-06-30 | 2023-07-02 | 2023-07-02 | 2 |  | 2023-07-05 | 2023-07-05 | Government of the Philippines (current year's budget) | 7762.2 | 7762.2 |  | 5400 | 5400 |  | 0.30432 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
6 | Office Supplies for the 20 August 2023 CSE PPT (New Five Star Trading & Printing Press) | MSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-07-04 |  | 2023-07-04 | N/A | 2023-07-04 |  | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 0 |  | 2023-07-12 | 2023-07-21 | Government of the Philippines (current year's budget) | 9067 | 9067 |  | 8010 | 8010 |  | 0.11658 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
7 | Office Supplies for the 20 August 2023 CSE PPT (Tacloban Tap Commercial) | MSD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | N/A | 2023-07-04 |  | 2023-07-04 | N/A | 2023-07-04 |  |  |  | 2023-07-10 | 2023-07-10 | 2023-07-10 |  |  | 2023-07-13 | 2023-07-13 | Government of the Philippines (current year's budget) | 12590 | 12590 |  | 10145 | 10145 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
8 | Office Supplies for the 20 August 2023 CSE PPT (Leyte Paperworld) | MSD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | N/A | 2023-07-04 |  | 2023-07-04 | N/A | 2023-07-04 |  | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 0 |  | 2023-07-25 | 2023-07-26 | Government of the Philippines (current year's budget) | 32234 | 32234 |  | 24272.5 | 24272.5 |  | 0.24699 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
9 | Office Supplies for the 20 August 2023 CSE PPT (Leyte Mightyt Minds Marketing) | MSD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | N/A | 2023-07-04 |  | 2023-07-04 | N/A | 2023-07-04 |  |  |  | 2023-07-10 | 2023-07-10 | 2023-07-10 |  |  | 2023-07-12 | 2023-07-12 | Government of the Philippines (current year's budget) | 7195 | 7195 |  | 2416.5 | 2416.5 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
10 | 2nd Quarter Office Supplies (Hand Soap, 10 pieces) Leyte Paperworld | MSD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | N/A | 2023-05-31 |  | 2023-05-31 | N/A | 2023-05-31 |  |  |  | 2023-07-18 | 2023-07-19 | 2023-07-19 |  |  | 2023-07-20 | 2023-07-20 | Government of the Philippines (current year's budget) | 3290 | 3290 |  | 690 | 690 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
11 | 2nd Quarter Office Supplies (Hand Soap, 10 pieces)-Sam's Trading | MSD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | N/A | 2023-05-31 |  | 2023-05-31 | N/A | 2023-05-31 |  |  |  | 2023-07-18 | 2023-07-19 | 2023-07-19 |  |  | 2023-11-20 | 2023-11-20 | Government of the Philippines (current year's budget) | 206112.44 | 206112.44 |  | 117016 | 117016
12 | 2nd Quarter Office Supplies (Hand Soap, 10 pieces)-ANDJ | MSD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | N/A | 2023-05-31 |  | 2023-05-31 | N/A | 2023-05-31 |  |  |  | 2023-07-18 | 2023-07-20 | 2023-07-20 |  |  | 2023-07-27 | 2023-07-27 | Government of the Philippines (current year's budget) | 48125 | 48125 |  | 31500 | 31500
13 | C Purlins 4x2x1.2 (Repair of CSC RO VIII Covered Walk)- Leyte Ever Hardware | MSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-07-11 |  | 2023-07-11 | N/A | 2023-07-11 |  | 0 |  | 2023-07-18 | 2023-07-19 | 2023-07-19 | 1 |  | 2023-07-24 | 2023-07-24 | Government of the Philippines (current year's budget) | 6400 | 6400 |  | 4400 | 4400 |  | 0.3125 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
14 | 3rd Quarter Office Supplies, Disinfectant Solution, 60 Gal and Stapler Standard, 10 pieces (Tac Tap Comm) | MSD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | N/A | 2023-07-25 |  | 2023-07-25 | N/A | 2023-07-25 |  |  |  | 2023-08-01 | 2023-08-03 | 2023-08-03 |  |  | 2023-08-16 | 2023-08-16 | Government of the Philippines (current year's budget) | 13500 | 13500 |  | 10230 | 10230 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
15 | 3rd Quarter Office Supplies (Tac Sam's Trading) | MSD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | N/A | 2023-07-25 |  | 2023-07-25 | N/A | 2023-07-25 |  |  |  | 2023-08-01 | 2023-08-03 | 2023-08-03 |  |  | 2023-11-20 | 2023-11-20 | Government of the Philippines (current year's budget) | 66750 | 66750 |  | 37165 | 37165 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
16 | General Pest and Termite Treatment (Mapecon Tacloban Inc) | MSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-07-25 |  | 2023-07-25 | N/A | 2023-07-25 |  |  |  | 2023-08-02 | 2023-08-04 | 2023-08-04 |  |  | 2023-10-03 | 2023-10-03 | Government of the Philippines (current year's budget) | 125000 | 125000 |  | 122500 | 122500 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
17 | Snacks in the conduct of TEA in Catarman, Northern Samar (Lucky's Catering Services) | FONS | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-01 |  | 2023-08-01 | N/A | 2023-08-01 |  | 0 |  | 2023-08-08 | 2023-08-10 | 2023-08-10 | 2 |  | 2023-08-15 | 2023-08-15 | Government of the Philippines (current year's budget) | 3000 | 3000 |  | 3000 | 3000 |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
18 | Snacks in the conduct of CSE-PPT in Catarman, Northern Samar (Lucky's Catering Services) | FONS | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-01 |  | 2023-08-01 | N/A | 2023-08-01 |  | 0 |  | 2023-08-08 | 2023-08-16 | 2023-08-16 | 8 |  | 2023-08-20 | 2023-08-20 | Government of the Philippines (current year's budget) | 12300 | 12300 |  | 12300 | 12300 |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
19 | Snacks and Meals in the conduct of CSE-PPT in Naval, Biliran (Weluisa Food Court) | FOBiliran | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-01 |  | 2023-08-01 | N/A | 2023-08-01 |  | 0 |  | 2023-08-08 | 2023-08-08 | 2023-08-08 | 0 |  | 2023-08-20 | 2023-08-20 | Government of the Philippines (current year's budget) | 20275 | 20275 |  | 18938 | 18938 |  | 0.065943 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
20 | Snacks and Meals in the conduct of TEA in Borongan City (Fredo's Restaurant) | FOES | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-01 |  | 2023-08-01 | N/A | 2023-08-01 |  | 0 |  | 2023-08-08 | 2023-08-08 | 2023-08-08 | 0 |  | 2023-08-20 | 2023-08-20 | Government of the Philippines (current year's budget) | 6500 | 6500 |  | 6500 | 6500 |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
21 | Snacks and Meals in the conduct of CSE-PPT in Borongan City (Fredos Restaurant) | FOES | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-01 |  | 2023-08-01 | N/A | 2023-08-01 |  |  |  | 2023-08-06 | 2023-08-08 | 2023-08-08 |  |  | 2023-08-20 | 2023-08-20 | Government of the Philippines (current year's budget) | 23375 | 23375 |  | 23375 | 23375 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
22 | Snacks and Meals in the conduct of CSE-PPT in Maasin City | FOSL | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-01 |  | 2023-08-01 | N/A | 2023-08-01 |  |  |  | 2023-08-08 | 2023-08-11 | 2023-08-11 |  |  | 2023-08-20 | 2023-08-20 | Government of the Philippines (current year's budget) | 26275 | 26275 |  | 26223 | 26223 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23 | Meals in the conduct of CSE-PPT in Catbalogan City (Toril Grill and Resto Bar) | FOSamar | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-01 |  | 2023-08-01 | N/A | 2023-08-01 |  | 0 |  | 2023-08-08 | 2023-08-08 | 2023-08-08 | 0 |  | 2023-08-20 | 2023-08-20 | Government of the Philippines (current year's budget) | 13050 | 13050 |  | 8700 | 8700 |  | 0.33333 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
24 | 1 Unit Four (4) Drawer Filing Cabinet | HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-01 |  | 2023-08-01 | N/A | 2023-08-01 |  |  |  | 2023-08-09 | 2023-08-10 | 2023-08-10 |  |  | 2023-08-15 | 2023-08-15 | Government of the Philippines (current year's budget) | 15000 | 15000 |  | 10500 | 10500 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25 | PCSA Tarpaulin | PALD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-01 |  | 2023-08-01 | N/A | 2023-08-01 |  |  |  | 2023-08-09 | 2023-08-10 | 2023-08-10 |  |  | 2023-08-17 | 2023-08-17 | Government of the Philippines (current year's budget) | 13680 | 13680 |  | 6080 | 6080 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
26 | Toner TN 323 for INEO 367 Photocopier | ESD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-08 |  | 2023-08-08 | N/A | 2023-08-08 |  |  |  | 2023-08-09 | 2023-08-10 | 2023-08-10 |  |  | 2023-08-15 | 2023-08-15 | Government of the Philippines (current year's budget) | 18000 | 18000 |  | 16500 | 16500 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
27 | Lunch to be served during the Shredding of Test Booklet on 20 August 2023 (Emmanuel's Place Enterprises) | ESD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-08 |  | 2023-08-08 | N/A | 2023-08-08 |  |  |  | 2023-08-09 | 2023-08-10 | 2023-08-10 |  |  | 2023-08-20 | 2023-08-20 | Government of the Philippines (current year's budget) | 3750 | 3750 |  | 3750 | 3750 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
28 | Asean Flag 1 piece (The Ultimate Music & Sports Studio) | MSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-08 |  | 2023-08-08 | N/A | 2023-08-08 |  |  |  | 2023-08-09 | 2023-08-09 | 2023-08-09 |  |  | 2023-08-10 | 2023-08-10 | Government of the Philippines (current year's budget) | 3500 | 3500 |  | 3000 | 3000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
29 | Snacks during the conduct of 20 August 2023 CSE-PPT in Tacloban City | FO-LEYTE 1 | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-08 |  | 2023-08-08 | N/A | 2023-08-08 |  |  |  | 2023-08-09 | 2023-08-10 | 2023-08-10 |  |  | 2023-08-20 | 2023-08-20 | Government of the Philippines (current year's budget) | 82500 | 82500 |  | 82500 | 82500 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
30 | Lunch for the conduct of TEA on July 26-27, 2023 | FO-LEYTE 1 | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-07-25 |  | 2023-07-25 | N/A | 2023-07-25 |  |  |  | 2023-07-26 | 2023-07-26 | 2023-07-26 |  |  | 2023-07-27 | 2023-07-27 | Government of the Philippines (current year's budget) | 3750 | 3750 |  | 3750 | 3750 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
31 | Plastic Certificate Holder | HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-07-18 |  | 2023-07-18 | N/A | 2023-07-18 |  |  |  | 2023-07-26 | 2023-07-27 | 2023-07-27 |  |  | 2023-07-28 | 2023-07-31 | Government of the Philippines (current year's budget) | 18000 | 18000 |  | 8000 | 8000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
32 | Transmitter and Receiver for CCTV | MSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-18 |  | 2023-08-18 | N/A | 2023-08-18 |  |  |  | 2023-08-18 | 2023-08-18 | 2023-08-18 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 9000 | 9000 |  | 8000 | 8000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
33 | Twin Head Rechargeable Emergency Light (2 Pieces)- Bosjan Main Mktg Corp | FOBiliran | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-15 |  | 2023-08-15 | N/A | 2023-08-15 |  |  |  | 2023-08-18 | 2023-08-18 | 2023-08-18 |  |  | 2023-09-01 | 2023-09-04 | Government of the Philippines (current year's budget) | 6000 | 6000 |  | 3900 | 3900 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
34 | Office Chairs (5 pieces) | LSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-15 |  | 2023-08-15 | N/A | 2023-08-15 |  |  |  | 2023-08-18 | 2023-08-18 | 2023-08-18 |  |  | 2023-09-11 | 2023-09-11 | Government of the Philippines (current year's budget) | 50000 | 50000 |  | 21875 | 21875 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
35 | 123erd PCSA Collaterals for Week 1 to 4 (Colored Tarpaulins) | PALD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-22 |  | 2023-08-22 | N/A | 2023-08-22 |  |  |  | 2023-08-25 | 2023-08-29 | 2023-08-29 |  |  | 2023-09-11 | 2023-09-12 | Government of the Philippines (current year's budget) | 13680 | 13680 |  | 6080 | 6080 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
36 | Office Supplies for the Medical Mission on 30 August 2023 (IDM) | LSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-22 |  | 2023-08-22 | N/A | 2023-08-22 |  |  |  | 2023-08-25 | 2023-08-25 | 2023-08-25 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 450 | 450 |  | 240 | 240
37 | Office Supplies for the Medical Mission on 30 August 2023 (Mercury Drugs Tac Sagkahan Branch) | LSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-22 |  | 2023-08-22 | N/A | 2023-08-22 |  |  |  | 2023-08-25 | 2023-08-25 | 2023-08-25 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 1950 | 1950 |  | 1144 | 1144 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
38 | Office Supplies for the Medical Mission on 30 August 2023 (IDM Supplies Trading) | LSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-22 |  | 2023-08-22 | N/A | 2023-08-22 |  |  |  | 2023-08-25 | 2023-08-25 | 2023-08-25 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 3800 | 3800 |  | 240 | 240 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
39 | Medical Equipment for the Medical Mission on 30 August 2023 | LSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A |  |  |  | N/A | [11 empty] | Government of the Philippines (current year's budget) | 0 |  |  | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
40 | Medical Equipment for the Medical Mission on 30 August 2023 (Berovan Mktg. Inc.) | LSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-22 |  | 2023-08-22 | N/A | 2023-08-22 |  |  |  | 2023-08-25 | 2023-08-25 | 2023-08-25 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 5000 | 5000 |  | 2045 | 2045 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
41 | Medical Equipment for the Medical Mission on 30 August 2023 (Innocare Pharma Medical Supplies Trading) | LSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-22 |  | 2023-08-22 | N/A | 2023-08-22 |  |  |  | 2023-08-25 | 2023-08-25 | 2023-08-25 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 5500 | 5500 |  | 2580 | 2580 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
42 | Meals and Snacks for the Conduct of the Medical Mission on 30 August 2023 (Emmanuel's Place Ent.) | LSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-22 |  | 2023-08-22 | N/A | 2023-08-22 |  |  |  | 2023-08-25 | 2023-08-25 | 2023-08-25 |  |  | 2023-08-30 | 2023-08-30 | Government of the Philippines (current year's budget) | 24600 | 24600 |  | 24600 | 24600 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
43 | Catering Services for the PCSA Kick Off (Ronn's Grilled Tuna & Sashimi) | PALD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-29 |  | 2023-08-29 | N/A | 2023-08-29 |  |  |  | 2023-08-31 | 2023-08-31 | 2023-08-31 |  |  | 2023-09-01 | 2023-09-01 | Government of the Philippines (current year's budget) | 3960 | 3960 |  | 3740 | 3740 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
44 | 2023 Plant Run Activity (Drinking Water, 350 ml 200 Bottles) | PSED | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-29 |  | 2023-08-29 | N/A | 2023-08-29 |  |  |  | 2023-09-11 | 2023-09-11 | 2023-09-11 |  |  | 2023-09-12 | 2023-09-12 | Government of the Philippines (current year's budget) | 3000 | 3000 |  | 2200 | 2200 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
45 | Supplies and Materials for the 2023 Plant-Run Activity (Board Paper, Board Stationary Paper) | PSED | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-29 |  | 2023-08-29 | N/A | 2023-08-29 |  |  |  | 2023-09-11 | 2023-09-11 | 2023-09-11 |  |  | 2023-09-13 | 2023-09-13 | Government of the Philippines (current year's budget) | 2025 | 2025 |  | 750 | 750 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
46 | T-Shirt 62 pieces for the 2023 Plant Run Activity (Raven's Printing Shop) | PSED | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-09-05 |  | 2023-09-05 | N/A | 2023-09-05 |  |  |  | 2023-09-11 | 2023-09-13 | 2023-09-13 |  |  | 2023-09-28 | 2023-09-28 | Government of the Philippines (current year's budget) | 31000 | 31000 |  | 29760 | 29760 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
47 | Catering Services for the conduct of the Media Blitz for the 123rd PCSA Activities promotion on 12 September 2023 | PALD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-09-08 |  | 2023-09-08 | N/A | 2023-09-08 |  |  |  | 2023-09-11 | 2023-09-11 | 2023-09-11 |  |  | 2023-09-12 | 2023-09-19 | Government of the Philippines (current year's budget) | 4500 | 4500 |  | 4350 | 4350 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
48 | Singlet for Plant-Run Activity 1 | PSED | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-09-08 |  | 2023-09-08 | N/A | 2023-09-08 |  |  |  | 2023-09-11 | 2023-09-13 | 2023-09-13 |  |  | 2023-09-28 | 2023-09-28 | Government of the Philippines (current year's budget) | 15000 | 15000 |  | 15000 | 15000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
49 | 123rd Philippine Civil Service Anniversary (PCSA) Tarpaulin- Pixel Eaters | PALD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-08 |  | 2023-08-08 | N/A | 2023-08-08 |  |  |  | 2023-08-09 | 2023-08-10 | 2023-08-10 |  |  | 2023-09-12 | 2023-09-12 | Government of the Philippines (current year's budget) | 13680 | 13680 |  | 6080 | 6080 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
50 | Certicate Holder A4 Size | PSED | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-09-05 |  | 2023-09-05 | N/A | 2023-09-05 |  |  |  | 2023-09-12 | 2023-09-12 | 2023-09-12 |  |  | 2023-09-13 | 2023-09-13 | Government of the Philippines (current year's budget) | 1800 | 1800 |  | 1560 | 1560 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
51 | Supplies for the 2023 Plant-Run Activity | PSED | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-09-29 |  | 2023-09-29 | N/A | 2023-09-29 |  |  |  | 2023-09-12 | 2023-09-13 | 2023-09-13 |  |  | 2023-09-13 | 2023-09-13 | Government of the Philippines (current year's budget) | 240 | 240 |  | 180 | 180 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
52 | Gardening Trowel, Water Sprinkler and Gloves | PSED | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-09-05 |  | 2023-09-05 | N/A | 2023-09-05 |  |  |  | 2023-09-13 | 2023-09-13 | 2023-09-13 |  |  | 2023-09-13 | 2023-09-13 | Government of the Philippines (current year's budget) | 9200 | 9200 |  | 5730 | 5730 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
53 | Singlet for Plant-Run Activity 2 | PSED | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-09-12 |  | 2023-09-12 | N/A | 2023-09-12 |  |  |  | 2023-09-13 | 2023-09-28 | 2023-09-28 |  |  | 2023-09-28 | 2023-09-28 | Government of the Philippines (current year's budget) | 26250 | 26250 |  | 23400 | 23400 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
54 | [25 empty] | 0 |  |  | 0
55 | Catering Services for the conduct of ORA-OHRA (Sept 28-29, 2023) and LACE (Dec 6-7, 2023)-Sefrem Event Catering Services | HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-08-29 |  | 2023-08-29 | N/A | 2023-08-29 |  |  |  | 2023-09-13 | 2023-09-20 | 2023-09-20 |  |  | 2023-09-28 | 2023-09-29 | Government of the Philippines (current year's budget) | 143000 | 143000 |  | 121000 | 121000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
56 | Meals in the conduct of 2023 CSC RO VIII Plant-Run Activity on 17 September 2023 (Emmanuel's Place Enterprises) | PSED | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-09-14 |  | 2023-09-14 | N/A | 2023-09-14 |  |  |  | 2023-09-15 | 2023-09-15 | 2023-09-15 |  |  | 2023-09-17 | 2023-09-17 | Government of the Philippines (current year's budget) | 5600 | 5600 |  | 5600 | 5600 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
57 | Catering Services for the Conduct of Dugong Buhay, Handog ng Lingkod Bayan:123rd PCSA Bloodletting Activity on 19 September 2023 (Emmnanuel's Place Enterprises) | MSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-09-12 |  | 2023-09-12 | N/A | 2023-09-12 |  |  |  | 2023-09-15 | 2023-09-15 | 2023-09-15 |  |  | 2023-09-19 | 2023-09-19 | Government of the Philippines (current year's budget) | 12000 | 12000 |  | 12000 | 12000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
58 | Catering Services for the Conduct of Dugong Buhay, Handog ng Lingkod Bayan:123rd PCSA Bloodletting Activity on 19 September 2023 (Optimuseats) | MSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-09-12 |  | 2023-09-12 | N/A | 2023-09-12 |  |  |  | 2023-09-18 | 2023-09-18 | 2023-09-18 |  |  | 2023-09-19 | 2023-09-19 | Government of the Philippines (current year's budget) | 8000 | 8000 |  | 6000 | 6000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
59 | Catering Services for the Conduct of the CSC RO VIII Strategic Planning and Budgeting on 21-22 September 2023 | PALD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-09-12 |  | 2023-09-12 | N/A | 2023-09-12 |  |  |  | 2023-09-15 | 2023-09-15 | 2023-09-15 |  |  | 2023-09-21 | 2023-09-22 | Government of the Philippines (current year's budget) | 43200 | 43200 |  | 42200 | 42200 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
60 | 3 Units Printer with Scanner | LSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-09-12 |  | 2023-09-12 | N/A | 2023-09-12 |  |  |  | 2023-09-15 | 2023-09-15 | 2023-09-15 |  |  | 2023-10-10 | 2023-10-10 | Government of the Philippines (current year's budget) | 28500 | 28500 |  | 26385 | 26385 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
61 | 2 Pieces Photocopier Toner | LSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-09-20 |  | 2023-09-20 | N/A | 2023-09-20 |  |  |  | 2023-09-29 | 2023-10-03 | 2023-10-03 |  |  | 2023-10-03 | 2023-10-03 | Government of the Philippines (current year's budget) | 8000 | 8000 |  | 6875 | 6875 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
62 | Catering Services for the conduct of ORA-OHRA on October 12-13, 2023 (Ryeoneth Catering Services and Restaurant) | HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-10-10 |  | 2023-10-10 | N/A | 2023-10-10 |  |  |  | 2023-10-11 | 2023-10-11 | 2023-10-11 |  |  | 2023-10-12 | 2023-10-13 | Government of the Philippines (current year's budget) | 71500 | 71500 |  | 66000 | 66000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
63 | 2 Pieces Plaque for the conduct of SESL on Nov 9-10, 2023 (PSED) | HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-10-10 |  | 2023-10-10 | N/A | 2023-10-10 |  |  |  | 2023-10-16 | 2023-10-17 | 2023-10-17 |  |  | 2023-10-17 | 2023-10-25 | Government of the Philippines (current year's budget) | 11000 | 11000 |  | 11000 | 11000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
64 | Customized Kit and Token for the conduct of the 2023 Service Excellence Summit for Leaders (SESL) on Nov 9-10, 2023 in Cebu City | HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-10-12 |  | 2023-10-12 | N/A | 2023-10-12 |  |  |  | 2023-10-18 | 2023-10-18 | 2023-10-18 |  |  | 2023-11-09 | 2023-11-10 | Government of the Philippines (current year's budget) | 630000 | 630000 |  | 599200 | 599200 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
65 | Acrylic Spray Paint, 10 pieces, Sand Paper #120, 10 pieces and Lacquer Thinner, 2 Bottles (Home Options, Inc.) | ESD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-10-10 |  | 2023-10-10 | 2023-10-10 | 2023-10-10 |  |  |  | 2023-10-16 | 2023-10-17 | 2023-10-17 |  |  | 2023-11-06 | 2023-11-06 | Government of the Philippines (current year's budget) | 3360 | 3360 |  | 1560 | 1560 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
66 | Office Supplies for the conduct of the 2023 Service Excellence Summit for Leaders in Cebu City on Nov. 9-10, 2023 in Cebu City (Ballpen 700 pieces)-Leyte Mighty Minds Mktg. | HRD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | N/A | 2023-10-12 |  | 2023-10-12 | N/A | 2023-10-12 |  |  |  | 2023-10-18 | 2023-10-19 | 2023-10-19 |  |  | 2023-10-23 | 2023-10-24 | Government of the Philippines (current year's budget) | 5600 | 5600 |  | 3500 | 3500 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
67 | Office Supplies for the conduct of the 2023 Service Excellence Summit for Leaders in Cebu City on Nov. 9-10, 2023 in Cebu City (Cert Holder, Specialty Paper)-New Five Star | HRD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | N/A | 2023-10-12 |  | 2023-10-12 | N/A | 2023-10-12 |  |  |  | 2023-10-18 | 2023-10-19 | 2023-10-19 |  |  | 2023-10-23 | 2023-10-24 | Government of the Philippines (current year's budget) | 20500 | 20500 |  | 11300 | 11300 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
68 | Lease of Venue and Catering Services for the conduct of the 2023 Service Excellence Summit for Leaders in Cebu City on Nov. 9-10, 2023 in Cebu City | HRD | No | NP-53.10 Lease of Real Property and Venue | N/A | N/A |  | N/A | N/A | 2023-10-10 |  | 2023-10-10 | N/A | 2023-10-17 |  |  |  | 2023-10-19 | 2023-10-19 | 2023-10-19 |  |  | 2023-11-09 | 2023-11-10 | Government of the Philippines (current year's budget) | 1904000 | 1904000 |  | 1903900 | 1903900 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
69 | Change Oil of CSC RO VIII Toyota Grandia and Two (2) Pieces Tires (Nicolas Tires) | MSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-10-10 |  | 2023-10-10 | N/A | 2023-10-10 |  |  |  | 2023-10-24 | 2023-10-25 | 2023-10-25 |  |  | 2023-11-03 | 2023-11-03 | Government of the Philippines (current year's budget) | 18900 | 18900 |  | 16984.8 | 16984.8 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
70 | Plaque for the 2023 SESL on Nov 9-10, 2023 in Cebu City (Tac Mabuhay Glass Supply) | HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-10-19 |  | 2023-10-19 | N/A | 2023-10-19 |  |  |  | 2023-10-24 | 2023-10-25 | 2023-10-25 |  |  | 2023-11-06 | 2023-11-06 | Government of the Philippines (current year's budget) | 14000 | 14000 |  | 11900 | 11900 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
71 | Plaque for the 2023 SESL on Nov 9-10, 2023 in Cebu City (Hanz Graphics Digital Imaging) | PALD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-10-24 |  | 2023-10-24 | N/A | 2023-10-24 |  |  |  | 2023-10-26 | 2023-10-27 | 2023-10-27 |  |  | 2023-11-04 | 2023-11-06 | Government of the Philippines (current year's budget) | 19800 | 19800 |  | 18700 | 18700 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
72 | Supplies for the conduct of the Prime-HRM Awarding Ceremony on 9 November 2023 in Cebu City (Double Sided Cert Holder, Frame for Cert 8.5x13 inches) | PSED | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-10-27 |  | 2023-10-27 | N/A | 2023-10-27 |  |  |  | 2023-10-31 | 2023-11-06 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 | Government of the Philippines (current year's budget) | 4000 | 4000 |  | 778 | 778 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
73 | Rental of LED Wall, Sounds and Lights on November 9 & 10, 2023 | HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-10-27 |  | 2023-10-27 | N/A | 2023-10-27 |  |  |  | 2023-10-31 | 2023-11-04 | 2023-11-04 |  |  | 2023-11-09 | 2023-11-10 | Government of the Philippines (current year's budget) | 150000 | 150000 |  | 150000 | 150000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
74 | 4th Quarter Office Supplies (New Five Star Trading & Printing Press) | MSD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | N/A | 2023-10-10 |  | 2023-10-10 | N/A | 2023-10-10 |  |  |  | 2023-11-15 | 2023-11-16 | 2023-11-16 |  |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 147700 | 147700 |  | 54300 | 54300 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
75 | 4th Quarter Office Supplies (Leyte Paperworld) | MSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-10-10 |  | 2023-10-10 | N/A | 2023-10-10 |  |  |  | 2023-11-15 | 2023-11-16 | 2023-11-16 |  |  | 2023-11-20 | 2023-11-20 | Government of the Philippines (current year's budget) | 0 |  |  | 20500 | 20500 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
76 |  |  | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-10-10 |  | 2023-10-10 | N/A | 2023-10-10 |  |  |  | 2023-11-15 | [6 empty] | Government of the Philippines (current year's budget) | 0 |  |  | 31600 | 31600 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
77 | AC Automatic Voltage Regulator (AVR) 1 Piece | ESD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-10-31 |  | 2023-10-31 | N/A | 2023-10-31 |  |  |  | 2023-11-17 | 2023-11-20 | 2023-11-20 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 6000 | 6000 |  | 2748 | 2748 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
78 | AC Automatic Voltage Regulator (AVR) 1 Piece | MSD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-10-31 |  | 2023-10-31 | N/A | 2023-10-31 |  |  |  | 2023-11-17 | 2023-11-20 | 2023-11-20 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 6000 | 6000 |  | 2748 | 2748 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
79 | Uninterruptible Power Supply 800 VA, Universal Outlets (2 units) | HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-11-28 |  | 2023-11-28 | N/A | 2023-11-28 |  |  |  | 2023-12-15 | 2023-12-21 | 2023-12-21 |  |  | 2023-12-27 | 2023-12-27 | Government of the Philippines (current year's budget) | 7000 | 7000 |  | 5000 | 5000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
80 |  |  | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A |  |  |  | N/A | [11 empty] | Government of the Philippines (current year's budget) | 0 |  |  | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
81 |  |  | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A |  |  |  | N/A | [11 empty] | Government of the Philippines (current year's budget) | 0 |  |  | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
82 |  |  | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A |  |  |  | N/A | [11 empty] | Government of the Philippines (current year's budget) | 0 |  |  | 0 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
83 | Meals in the conduct of 2023 CSC RO VIII IAT Audit Closing Meeting on December 18, 2023 | ESD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-11-28 |  | 2023-11-28 | N/A | 2023-11-28 |  |  |  | 2023-12-15 | 2023-12-21 | 2023-12-21 |  |  | 2023-12-27 | 2023-12-27 | Government of the Philippines (current year's budget) | 4875 | 4875 |  | 4700 | 4700 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
84 | Catering Services for the Family Day on December 15, 2023 and Staff Development Activity and Pasidungog on December 16, 2023 | HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-12-11 |  | 2023-12-11 | N/A | 2023-12-11 |  |  |  | 2023-12-15 | 2023-12-15 | 2023-12-15 |  |  | 2023-12-18 | 2023-12-19 | Government of the Philippines (current year's budget) | 150600 | 150600 |  | 131170 | 131170 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed
85 | Grazing Table for December 16, 2023 (Staff Dev Activity and Pasidungog) | HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-12-11 |  | 2023-12-11 | N/A | 2023-12-11 |  | 0 |  | 2023-12-15 | 2023-12-15 | 2023-12-15 | 0 |  | 2023-12-18 | 2023-12-19 | Government of the Philippines (current year's budget) | 32000 | 32000 |  | 20000 | 20000 |  | 0.375 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
86 | Backdrop and Decoration (Family Day and Staff Dev Activity and Pasidungog) | HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | N/A | 2023-12-11 |  | 2023-12-11 | N/A | 2023-12-11 |  | 0 |  | 2023-12-15 | 2023-12-15 | 2023-12-15 | 0 |  | 2023-12-18 | 2023-12-19 | Government of the Philippines (current year's budget) | 15000 | 15000 |  | 15000 | 15000 |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
[26 empty] | 0 |  |  | 0 |  |  | -
[26 empty] | 0 |  |  | 0 |  |  | -
[25 empty] | Total Allotted Budget of Procurement Activities | 4682581.24 | 4682581.24 | 0 |  |  |  | 9.246%
[25 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 4249610.4 | 4249610.4 | 0
[25 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 432970.84 | [14 empty] | 2023-06-30
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column42
ONGOING PROCUREMENT ACTIVITIES | [31 empty] | -
1 | Provision of FY 2024 Security Services for CSC RO VIII | MSD | Yes | Competitive Bidding | N/A | 2023-11-15 |  | N/A |  | 2023-12-06 | 21 | 2023-12-07 | 2023-12-12 | 2023-12-12 | 6 | 6 | 27 | [8 empty] | 800000 | 800000 |  | 772747.32 | 772747.32 |  | 0.034066 |  | N/A |  | 2023-12-06 | 2023-12-07 | 2023-12-12 |  | Ongoing Procurement Process | -138
2 | Bottom Load Hot and Cold Water Dispenser 1 unit | FOES | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A |  | 2023-11-28 |  | 2023-11-28 | N/A | 2023-11-28 |  |  |  | 2023-12-15 | 2023-12-21 | 2023-12-21 | [5 empty] | 18000 | 18000 |  | 11687 | 11687 | [9 empty] | Ongoing Procurement Process
3 | Gas Tank 11 kg, LPG Regulator, 2 meters Hose | FO-LEYTE 1 | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A |  | 2023-11-28 |  | 2023-11-28 | N/A | 2023-11-28 |  |  |  | 2023-12-15 | 2023-12-21 | 2023-12-21 | [5 empty] | 4800 | 4800 |  | 3646 | 3646 | [9 empty] | Ongoing Procurement Process
4 | Standard Industrial Metal Electric Standfan (2 units) | FONS | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A |  | 2023-11-28 |  | 2023-11-28 | N/A | 2023-11-28 |  |  |  | 2023-12-15 | 2023-12-21 | 2023-12-21 | [5 empty] | 5000 | 5000 |  | 3470 | 3470 | [9 empty] | Ongoing Procurement Process
-
-
-
-
-
[7 empty] | #DIV/0! | [17 empty] | Total Allotted Budget of On-going Procurement Activities | 827800 | 827800 | 0 | 791550.32 | 791550.32 | 0 | 3.407%
|  | Prepared by: | [9 empty] | Recommended for Approval by: | [16 empty] | APPROVED:
|  | Signed |  |  | Signed | [6 empty] | Signed | [16 empty] | Signed
|  | CRISANTO H. CORTES |  |  | MA. LOURDES H. SABALZA | [6 empty] | ATTY. FLORDELIZA C. ALGAS | [16 empty] | ATTY. MARILYN E. TALDO
|  | Administrative Officer IV |  |  | Senior Human Resource Specialist | [6 empty] | Director III | [16 empty] | Director IV
|  | BAC Secretariat | [9 empty] | BAC Chairperson | [16 empty] | Head of the Procuring Entity

## Tool 1-Processing (hidden)
Summary of Information for Processing of IRPP
Indicator 1: % of Processed Procurement Activities vs Planned in terms of amount |  | #REF!
Formula | Value | Remarks
Total Amount of APP as updated | #REF!
Divide by: Total Amount of ABC of procurement activities started | #REF! | ABC of awarded + ABC of on-going procurement projects (less ABC of Failure of Bids)
Indicator 2: Average % of Variance Between Contract Amount vs Approved Budget for the Contract |  | #REF!
Particular | Value | Remarks
Total Amount of ABC of procurement activities started | #REF!
Total Contact Cost | 4251874.8
Total Variance for Each Awarded Procurement Project | #REF! | Column shall be hidden
Divide by Number of Awarded Procurement Projects | 85
Indicator 3. Timeliness on the Conduct of Procurement
|  | Indicator 3.1 Average No. of Days to commence procurement (Pre-Proc to Posting of IB) |  | Indicator 3.2: Average No. of Days to open bid proposals (Posting of IB/ to Opening of Bids) |  | Indicator 3.3: Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) |  | Indicator 3.4: Average Number of Days to Conclude Procurement (Posting of IB to Recommend Award) |  | Indicator 3.5: Average Number of Days to Issue Notice to Proceed (from Issuance of NOA to Issuance of NTP) |  | Indicator 3.6: Accumulated Number of Days for the Procurement Process (Posting of IB to NTP)
Mode of Procurement | Total No. of Activities under subject modality | Total No. of Days from PreProc to IB | Average Days from Pre-Proc to Posting of IB | Total No. of Days from IB to Opening | Average Days from Posting of IB to Opening of Bids | Total No. of Days Opening to Recommend Award) | Average Days from Opening of Bids to Recommend Award | Total No. of Days from Posting of IB to Recommend Award | Average Days from Posting of IB to Recommend Award | Total No. of Days from Issuance of NOA to Issue NTP | Average Days from NOA to NTP | Total No. of Days from Posting of IB to Issue NTP | Average Days from Posting of IB to NTP
Competitive Bidding | 1 | 0 | 0 | 21 | 0 | 6 | 6 | 27 | 27 | 0 | 0 | 0 | 0
Limited Source Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Direct Contracting | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Repeat Order | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0.13333 | 0 | 0
NP-53.1 Two Failed Biddings | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.2 Emergency Cases | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.3 Take-Over of Contracts | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.5 Agency-to-Agency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.7 Highly Technical Consultants | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.9 - Small Value Procurement | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0.14667 | 0 | 0
NP-53.10 Lease of Real Property and Venue | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP-53.11 NGO Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.12 Community Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Emergency Procurement under Bayanihan Act | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Alternative Method | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 92 | 0 | 0 | 0.91304 | 0 | 0.26087 | 1.5 | 1.1739 | 6.75 | 0.56522 | 0.07 | 0 | 0
*formula for days interval for each procurement activity for each indicator are embedded in the PMR.
Indicator 4. Percentage of Amount and Volume by Tender and Award of Procurement Activities per Mode of Procurement
Mode of Procurement | Total No. of Activities | Total Number of Awarded | Total ABC | Total Contract Cost | %Vol of Awarded | %ABC of Awarded | Total Number of Failed | ABC of Failed
Competitive Bidding | 1 | 0 | 0 | 0 | 0% |  | 0 | 0
Limited Source Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Direct Contracting | 0 | 0 | 0 | 0 |  |  | 0 | 0
Repeat Order | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 15 | 15 | 748914.24 | 465483 | 100% | 62.15% | 0 | 0
NP-53.1 Two Failed Biddings | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.2 Emergency Cases | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.3 Take-Over of Contracts | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.5 Agency-to-Agency | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.7 Highly Technical Consultants | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.9 - Small Value Procurement | 75 | 69 | 2057467 | 1882491.8 | 92% | 91.5% | 0 | 0
NP-53.10 Lease of Real Property and Venue | 1 | 1 | 1904000 | 1903900 | 100% | 99.99% | 0 | 0
NP-53.11 NGO Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.12 Community Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 | 0 | 0 |  |  | 0 | 0
Emergency Procurement under Bayanihan Act | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Alternative Method | 0 | 0 | 0 | 0 |  |  | 0 | 0
Total | 92 | 85 | 4710381.24 | 4710381.24 | 73% | 84.55% | 0 | 0
Total for Alternative Mode of Procurement | 91 | 85 | 4710381.24 | 4251874.8 | 97.33% | 84.55% | 0 | 0
Indicator 5: Accumulated No. of Days for On-going Procurement Activities
Timeline | No. of Procurement Activities | %
Exceeds 180 days | 0 | 0%
Within 91 to 180 days | 0 | 0%
Within 45 to 90 days | 0 | 0%
Within 0 to 44 days | 0 | 0%
Total | 0 | 0%
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 6. Distribution of On-going, Awarded, and Failed procurement Activities
Status | No. of Procurement Activities | % by No. of Procurement of Activities | ABC Amount of Activities | % by ABC | Contract Cost | Contract/ABC | Variance
Awarded | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Completed | 81 | 95.29% | 4427893.8 | 84.25% | 4097040.8 | 83.81% | 0.07472
Failed | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Ongoing | 4 | 4.706% | 827800 | 15.75% | 791550.32 | 16.19% | 0.04379
Total | 85 | 100% | 5255693.8 | 100% | 4888591.12 | 100% | 0.069849
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 7a: % of Number of Procurement activities conducted under early procurement |  |  | 1.087%
Indicator 7b: % of ABC of Procurement activities conducted under early procurement |  |  | 14.52%
Particular | No. of Procurement Activities | ABC Amount of Activities
Under EPA | 1 | 800000
Regular Procurement | 91 | 4710381.24
Total | 92 | 5510381.24
Indicator 8a: Percentage of Number of Awarded Contracts under EPA |  |  | 0%
Indicator 8b: Percentage of Contract Cost of EPA against the total ABC under EPA |  |  | #VALUE!
Formula | No. of Procurement Activities | Amount of ABC Procurement Activities | Contract Cost of Procurement Activities | Percentage Variance
Total Contracts Awarded under EPA* | 0 | 0 | 0 | 0%
Total Contracts Completed under EPA* | 0 | 0 | 0 | 0%
Total Failed Bid under EPA* | 0 | 0 | 0 | 0%
Total Ongoing Activities under EPA* | 1 | 800000 | #VALUE! | #VALUE!
Total Procurement Activities under EPA | 1 | 800000 | #VALUE!
To compute for the total, a separate sheet may be created of the PMO may simply filter the cells to capture the total number.
Indicator 9: Stages where failure of bidding are encountered
Particular | No. of Procurement Activities | Amount of ABC | Vol. % | Amount %
Invitation To Bid | 0 | 0 | 0% | 0%
Pre-bidding Conference | 0 | 0 | 0% | 0%
Opening of Bids | 0 | 0 | 0% | 0%
Bid Evaluation | 0 | 0 | 0% | 0%
Post-Qualification | 0 | 0 | 0% | 0%
BAC Resolution | 0 | 0 | 0% | 0%
Award | 0 | 0 | 0% | 0%
Cancelled | 0 | 0 | 0% | 0%
TOTAL | 0 | 0

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget)
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget)
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget)
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution
Failed under Section 35.1 (b) |  | BAC Resolution
Failed under Section 35.1 (c) |  | Award
Failed under Section 41 (b) |  | Cancelled
Failed under Section 41 (c)
Contract was extended
Contract was renewed
Cancelled
Others, please encode directly on the cell